## Progress Schedule (revised annu
Bay TMDL 2026 Progress Schedule
Legend: | BMP Items
QAPP Items
Task Decription | Responsible Party | Task Start Date | Task due Date | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01
Annual Progress Reporting Appendix Draft: BMP Listing, descriptions, and mapping adjustments are due from jurisdictions for any BMPs that will be submitted for progress assessment that are not already included in the Annual Progress Reporting Appendix. An initial draft is sent in July to the WTWG for input. | Jurisdictions | 2026-07-01 | 2026-07-31 | bar: 2026-07-01
Annual Progress Reporting Appendix Draft Review: Final jurisdictional requests for Annual Progress Reporting Appendix adjustments received for inclusion consideration. The August 7th Watershed Technical Workgroup will provide a forum for the review of the 2026 Progress Annual Progress Reporting Appendix that includes consideration edits received since the previous progress year. Final feedback will need to be received by email prior to August 31, 2026. This task due date of August 31 is to allow a day to finalize this product internally and integrate it into CAST. | Jurisdictions | 2026-08-01 | 2026-08-31 | bar: 2026-08-01
Initial Updated Quality Assurance Project Plans (QAPPs) Due: This first draft with initial updates should address any unresolved revision requests made in the Final 2025 Progress QAPP Review Letters. Changes since the previous progress year in field, laboratory, quality control, and/or data management procedures must also be reported in this QAPP. Highlight or otherwise flag these changes from the previous progress year's approved version, and submit documentation (i.e. email) to Auston Smith (smith.auston@epa.gov), and Durga Ghosh (dghosh@usgs.gov) confirming a review was conducted. Partners must notify the project officer prior to this deadline if changing the number of samples, the number of sites, or parameters measured in an accepted QAPP methodology.Additionally, updates describing new programs and/or data sources and changes to methods of tracking, reporting, and verification are due by September 1st in any associated QAPP Appendices or attached plans. At the September 3rd WTWG, the receipt of these QAPPs will be confirmed for review to begin. If there are no changes, the recipient must provide written documentation (i.e. email) to Auston Smith (smith.auston@epa.gov), cc Durga Ghosh (dghosh@usgs.gov) confirming a review was conducted and no changes have occurred. | Jurisdictions | N/A | 2026-09-01 | bar: 2026-07-01 to 2026-09-01
Federal Agency Data Submitted to Jurisdictions for Annual Progress Submissions: Federal agencies should submit all relevant datasets of BMP data to relevant jurisdictions by the October deadline to allow for jurisdictions to have adequate time to incoorporate these datasets into their aggregated submissions. | Federal Agencies | N/A | 2026-10-01 | bar: 2026-08-01 to 2026-10-01
Submit Scenario Land Use Datasets: At the November 5th WTWG, the receipt of these datasets will be confirmed so CAST scenario setup can continue. 1) permitted forest harvest acres, 2) continually disturbed and permitted construction acres – including estimates of any unpermitted acres 3) CAFO/AFO animal splits by county 4) Desired acreages for Hay and Pasture High | Jurisdictions | 2026-08-01 | 2026-11-02 | bar: 2026-08-01 to 2026-11-01
Annual Progress Reporting Appendix Finalization: CBPO will finalize the Annual Progress Reporting Appendix for BMP submissions on September 1 and circulate that via email to workgroup membership and will also be posted on CAST here: https://cast.chesapeakebay.net/Home/TMDLTracking#progressReportingSection This finalized version of the Annual Progress Reporting Appendix for 2026 progress and any major changes since the previous progress year will be presented at the September 3rd WTWG. | CBPO | N/A | 2026-09-01 | bar: 2026-09-01
Jurisdictions Submit BMP Implementation Data to Progress Reporting Portal: Assuming LU and Animal Data has been received, this submission process will be ongoing from September 1 -December 1. The expectation is that December 1st will be last submission prior to the initial review of jurisdictional data. During WTWG meetings during this period, CBPO will provide updates on received land use and BMP data. BMPs should be submitted by this due date for the July 1 to June 30 2026 period from jurisdictions for the 2026 Progress Phase 6 model assessment – both wastewater data and non-wastewater BMPs. Validation reports will be available before December 1 and are available upon request from Jessica Rigelman (jrigelman@j7llc.com). Scenarios with loads will be run after December 1st to allow time for this year's final land use to be prepared and incorporated into CAST. Please copy Auston (smith.auston@epa.gov) on all communication on submitted data. These submitted datasets should address refinement comments received from previous progress scenarios and review(s). | Jurisdictions | 2025-09-01 | 2026-12-01 | bar: 2026-09-01 to 2026-12-01
Jurisdictions Submit QAPP Refinements: EPA requests for refinement of QAPP details from the initial Sept 1 submission (Version 1) must be addressed by Dec 1. Updated QAPP submissions are due December 1, but can be submitted earlier. Additional revisions between Dec.1 and the ultimate Monday, Feb 8, 2027 deadline may be necessary as a result of verification discussions and progress scenario review. These updates should address any unresolved revision requests made since the initial QAPP update due September 1, 2025. Among other requested additions, these updates should describe new data sources, programs and methodologies for tracking, reporting, and verification for 2026 Progress. | Jurisdictions | 2025-09-01 | 2025-12-01 | bar: 2026-09-01 to 2026-12-01
Jurisdictions Submit Point Source Data via Point Source Data Submission Application: 1) Biosolid mass and nutrient concentration application 2) CSO connections and pass-through data, 3) Large monitored onsite septic system load data (commercial and residential) 4) Rapid infiltration basin load data (RIBs) 5) Ag and Urban spray irrigation 6) Flow Splits 7) WTWP flow and concentration data | Jurisdictions | 2025-09-01 | 2025-12-01 | bar: 2026-09-01 to 2026-12-01
CBPO Scheduling for Initial Verification Discussions: Auston Smith will send out scheduling poll emails in October to ensure initial verification calls can be held with all jurisdictions the week of December 14-18th. Please reply to the scheduling poll ASAP to ensure members of your team can be available during the week of December 14-18th. Please flag in advance if this is not possible. Verification Agendas will be attached to the meetings based on December 1st COB rerun data. As flagged below, follow up verification discussions will be held as necessary. | CBPO and Jurisdictions | 2026-11-01 | 2026-12-01 | bar: 2026-10-01 to 2026-12-01
Initial CBPO-Jurisdiction Scheduled Verification Calls: CBPO will have the initial scheduled verification discussions with jurisdictions to discuss BMP and wastewater trends of note, and QAPP status. Agendas outlining QAPP questions, BMP questions, and point source facilities for discussion will be included on the meeting invite. Data submitted by Dec 1st will be reviewed and any additional datasets or submission adjustments submitted post-Dec 1 will be discussed in January of the next year. This will allow all the most recent datasets for progress to be submitted, and a thorough review of data as it is available in CAST to meet the early February deadline in row 17. | CBPO and Jurisdictions | 2025-12-14 | 2025-12-18 | bar: 2026-12-01
CAST Reports available for Jurisdictional Review and Feedback: Reporting of revised data following the initial Dec 1 submission, which is used for the initial verification discussion, are due by 12pm EST each Friday during this window to be integrated . Follow-up verification calls to address questions will be scheduled during this period as needed. New reports for 2026 progress will be run each Friday and will be available the following Monday. In some cases the reports may be available earlier; jurisidictions have the option to check on the report completion status as needed. | CBPO and Jurisdictions | 2025-12-01 | 2027-02-08 | bar: 2026-12-01 to 2027-02-01
QAPP Outstanding Comments Response due: It is expected that jurisdictions address all outstanding EPA QAPP review comments in their Review Letters by this date. Addressing these comments and any corresponding progress submission data problems should occur no later than February 5 to ensure full credit of quality data prior to the scenario finalization. | EPA and Jurisdictions | 2025-12-01 | 2026-02-05 | bar: 2026-12-01 to 2027-02-01
Final 2025 Progress Run Available: All updates to BMP data must be submitted by this deadline to ensure a final progress run can be provided to jurisdictions to close the process for that particular progress year. The scenario should be available to Progress Buddies within a week of finalization unless there are outstanding items noted. Additional changes to the scenario will be noted for the WTWG. | CBPO | N/A | 2026-02-12 | bar: 2027-02-01
Final Review of Jurisdictional QAPPs and Approval Memos Issued: This memo summarizes jurisdictional QAPP approval status for the relevant Progress year and tracks the status of revision requests between EPA CBPO and jurisdictions. In addition, the memo documents any outstanding revision requests expected for the subsequent progress year submission in September 2026. | EPA | 2025-02-08 | 2026-03-05 | bar: 2027-02-01 to 2027-03-01
2025 Progress Finalized and Released on CAST: Following finalization of communication surrounding 2026 progress by the CBPO Web Team and EPA Indicators Team, the final progress scenario will be released on CAST for public use first week of May. | CBPO | 2026-02-12 | 2026-05-07 | bar: 2027-02-01 to 2027-05-01
Disclaimer: As with some past progress scenarios (2025), the finalization of 2026 Progress may be delayed due to provide adequate time to address unresolved issues surrounding data submissions and verification assessments. The Bay Program Office staff will attempt to stay on schedule and will update jurisdiction technical teams directly on progress. Any updates on the schedule will be provided at the Watershed Technical Work Group (WTWG) monthly meetings.