## Sheet1
Bay TMDL 2023 Progress Schedule
Legend: | BMP Items
QAPP Items
Task Decription | Responsible Party | Task Start Date | Task due Date | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01
NEIEN Appendix Draft: BMP Listing, descriptions, and mapping are due from jurisdictions for any proposed BMPs that will be submitted for progress assessment that are NOT included in the NEIEN Appendix. An initial draft will be presented on the July 6th WTWG for review. | Jurisdictions | 2023-07-01 | 2023-07-31 | bar: 2023-07-01
NEIEN Appendix Review: Final jurisdictional requests for NEIEN Appendix adjustments received for inclusion consideration. A second draft will be presented in August 3rd WTWG and will incorporate further changes into final version. | Jurisdictions | 2023-08-01 | 2023-08-17 | bar: 2023-08-01
NEIEN Appendix Finalization: CBPO will finalize the NEIEN Appendix for BMPs receiving credit and that version will be posted on CAST here: https://cast.chesapeakebay.net/Home/TMDLTracking#progressReportingSection Send out link to jurisdictions | CBPO | 2023-08-18 | 2023-08-31 | bar: 2023-08-01
Initial Updates to QAPPs Due: These initial updates should address any unresolved revision requests made in the Final 2022 Progress QAPP Review Memos. Changes in field, laboratory, quality control, or data management procedures must be reported in the QAPP to the CBPO by September 1st. Additionally, updates to jurisdictions’ BMP Verification Program Plans (VPPs) describing new data sources and changes to methods of tracking, reporting, and verification are due by September 1. If there are no changes, the recipient must provide written documentation (i.e. email) to the project officer, cc Durga Ghosh (dghosh@chesapeakebay.net) confirming a review was conducted and no changes have occurred. The recipient must notify the project officer prior to changing the number of samples, the number of sites, or parameters measured. | Jurisdictions | N/A | 2023-09-01 | bar: 2023-08-01
Land Use Data Submissions Due for the Following Datasets: 1) permitted forest harvest acres, 2) continually disturbed and permitted construction acres – including estimates of any unpermitted acres and 3) CAFO/AFO animal splits by county within the CB Watershed | Jurisdictions | 2023-08-01 | 2023-11-01 | bar: 2023-08-01 to 2023-10-01
Jurisdictions Can Submit BMP Implementation Data to NEIEN: Assuming LU and Animal Data has been received, this review process will be ongoing from September 1 -December 1. Expectation is that December 1 will be final submission for jurisdictional data. BMPs should be submitted by this due date for the July 1 to June 30 period from jurisdictions for the 2023 Progress Phase 6 model assessment – both wastewater data and non-wastewater BMPs. Scenarios before December 1st are available upon request from Jessica Rigelman. Please build in time for communication on submitted data. This final submission should address comments received from previous review(s). | Jurisdictions | 2023-09-01 | 2023-12-01 | bar: 2023-09-01 to 2023-11-01
Jurisdictions Submit Associated QAPP Refinement: Requests for refinement for jurisdictional QAPPs must be addressed and updated versions submitted by December 1st. These updates should address any unresolved revision requests made since the initial QAPP update due September 1. These updates should describe new data sources and methodologies for tracking, reporting, and verification for 2023 Progress. Final QAPP submissions are due Dec. 1, additional revisions post-December 1 may be necessary as a result of EPA review. Please build in time for communication on submitted data. | Jurisdictions | 2023-09-01 | 2023-12-01 | bar: 2023-09-01 to 2023-11-01
Point Source Data Submission due to CBPO via Point Source Data Submission Tool 1) Biosolid and ag spray irrigation mass and nutrient concentration application by count, 2) CSO connections and pass-through data, 3) Large monitored onsite septic system load data (commercial and residential) 4) Rapid infiltration basin load data (RIBs) | Jurisdictions | 2023-09-01 | 2023-12-01 | bar: 2023-09-01 to 2023-11-01
QAPP Meeting to Discuss Updates By December 11th, CBPO will reach out to each jurisdiction to schedule initial meetings with each jurisdiction. Other meetings to discuss QAPP updates and associated BMP data can be scheduled as needed. | CBPO | 2023-12-01 | 2023-12-11 | bar: 2023-12-01
CAST Reports available for Jurisdictional Review and Feedback Submissions of revised data for a new report are due by 12pm EST each Friday during this window. Follow-up calls with State Technical Leads to sort out potential errors for reports are available during this period as needed. December 1, 2023 is a Friday, so reports will be run that day and then will be available on Monday, December 4th. The expectation is that reports will be run on Fridays and will be available the following Monday. | CBPO and Jurisdictions | 2023-12-01 | 2024-02-07 | bar: 2023-12-01 to 2024-01-01
QAPP Outstanding Comments Response due: It is expected that jurisdictions address all outstanding comments on their BMP Verification Program Plans from EPA. Addressing these comments and data problems should occur after submission of the BMP data and EPA’s review of progress but by no later than February 9th of each year to ensure full credit of quality data. | CBPO and Jurisdictions | 2023-12-01 | 2023-02-09 | bar: 2023-12-01 to 2024-02-01
Final 2023 Progress Run Available All updates to BMP data must be submitted by this deadline to ensure a final progress run can be provided to jurisdictions before progress is finalized. | CBPO and Jurisdictions | 2023-12-01 | 2023-02-09 | bar: 2023-12-01 to 2024-02-01
Final Review of Jurisdictional QAPPs and Approval Memos Issued This memo summarizes the effort taken by jurisdictions to submit their data on time for annual progress. Signed versions of the jurisdictional QAPPs will be provided at this time. | EPA | 2023-02-24 | 2023-03-08 | bar: 2024-02-01 to 2024-03-01
2023 Progress Finalized and Released on CAST Following finalization by the CBPO Web Team, the final progress scenario will be released on CAST for public use. | CBPO | 2023-03-09 | 2023-03-21 | bar: 2024-03-01
Formal Verification Letters sent out to States by Bay Program Office This letter confirms that jurisidctions have completed the verification process for annual progress. The process should not be seen as complete until this letter is received. | EPA | 2023-01-15 | ~May | bar: 2024-02-01 to 2024-05-01
Disclaimer: As with 2022 Progress, the finalization of 2023 Progress may be delayed due to provide adequate time to address unresolved issues surrounding the verification assessments. The schedule may need to be altered to accommodate the availability of jurisdictional representatives and/or to accommodate the delays mentioned above. The Bay Program Office Staff will attempt to stay on schedule and will update jurisdiction technical teams directly on progress. Any updates on the schedule will be provided at the Watershed Technical Work Group (WTWG) monthly meetings.